{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["工作表1"],"not_rendered":{"external_links":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"工作表1","index":0,"n_rows":32,"n_cols":7,"rows_kept":32,"merged":[[1,0,1,6],[3,0,3,6],[4,0,4,6],[6,0,6,6],[8,0,8,6],[20,0,20,6],[28,0,28,6],[30,0,30,6]],"flags":["formulas_cached_only"]}
[null,"附件3："]
["三河市2015年—2017年清洁能源替代重点项目汇总表"]
["序号","项目名称","项目单位","总投资（万元）","主要建设内容","完成时限","备注"]
["一、供热能力提升项目"]
["（一）热电联产项目"]
[1,"三河电厂三期热电联产扩建项目","三河发电有限责任公司",303000,"安装2台350MW热电联产机组，同步建设高效除尘、烟气脱硫、脱硝等多污染物脱除设施。","2018-10-01"]
["（二）余热余压利用项目"]
[1,"350MW机组余热余压综合利用技改工程","三河发电有限责任公司",19820,"三河电厂一期#1、#2机组采用10台36MW吸收式热泵和1台22MW背压式发电机组，充分回收利用循环冷却水余热和采暖抽汽余压","2016-08-01"]
["（三）供热管网改造项目"]
[1,"滨河院、油库院集中供暖工程","三河市热力总公司",2650,"解决滨河院、油库院集中供热问题，建设3座热力站敷设管道约5万米。","2016-10-01"]
[2,"兴元商贸城集体供暖工程","三河市热力总公司",111,"解决兴元商贸城集中供暖问题","2015-10-01"]
[3,"2015年热力一厂外网改造工程","三河市热力总公司",133,"解决热力一厂供暖，劳动局主管道区域二级供热管网及庭院管网失水严重的问题，保障锅炉正常运行，提高供暖质量。","2015-10-01"]
[4,"2015年信合一次网、汽车门店二次管网改造工程","三河市热力总公司",146,"解决信合小区等地区一次管网糟腐导致严重失水问题，保障锅炉正常运行，提高供暖质量。","2015-10-01"]
[5,"2015年世纪花苑南区外网改造工程","三河市热力总公司",72,"解决世纪花苑南区管网糟腐导致严重失水的问题，保障锅炉正常运行,提高供暖质量。","2015-10-01"]
[6,"美食城周边管网改造工程","三河市热力总公司",147,"美食城周边管段使用年限已超过十五年，为保障美食城及周边正常供暖需要更换。","2015-10-01"]
[7,"2015年热力管理四处管网改造工程","三河市热力总公司",149,"解决公园至公园管理处，工商局及家属楼，四季阳光二期管道糟腐严重问题，提高供暖质量。","2015-10-01"]
[8,"热力二厂过河管道改造工程","三河市热力总公司",800,"对热力二厂过河管道更换","2016-10-01"]
[9,"燕郊供热老旧管网改造项目","燕郊高新区管委会",810,"改造16条老旧管线；安装9800米管线，718只阀门，388座阀门检查井。","2015-10-01"]
[10,"华信小区、理想新城、福鼎庄园热计量收费改造工程","三河市热力总公司",143.5,"对华信小区、理想新城、福鼎庄园部分住户进行热计量改造。","2016-10-01"]
[11,"银燕二期、四季阳光一期、东风公寓热计量收费工程","三河市热力总公司",149.5,"对银燕二期、四季阳光一期、东风公寓进行热计量改造。","2016-10-01"]
["二、燃煤锅炉改造项目"]
[1," 华北科技学院燃煤锅炉改造项目 ","燕郊高新区管委会",200,"彻底淘汰现有锅炉6台，共计40蒸吨，现有27万平米供热面积全部并入市政供热管网。","2015-04-01"]
[2," 防灾科技学院燃煤锅炉改造项目","燕郊高新区管委会",200,"彻底淘汰现有锅炉4台，共计29蒸吨，现有13万平米供热面积全部并入市政供热管网。","2015-10-01"]
[3,"三河市医院燃煤锅炉改造项目","三河市环保局",100,"彻底淘汰现有锅炉4 台，共计10 蒸吨，现有 2.2万平米供热面积全部并入市政供热管网。","2015-10-01"]
[4,"三河市中医院燃煤锅炉改造项目","三河市环保局",50,"彻底淘汰现有锅炉 1台，共计2 蒸吨，现有0.4 万平米供热面积全部并入市政供热管网。","2015-10-01"]
[5,"25家事业单位煤改气项目","三河市环保局",2000,"燕京技术学院等25事业单位现有28台燃煤锅炉全部替换成燃气锅炉","2015-10-01"]
[6,"燕郊福成小区“电能替代”工程","燕郊福成小区物业公司",800,"彻底淘汰现有燃煤锅炉6台，共计25蒸吨，为8000余户居民安装电热水器。","2015-06-01"]
[7,"市供电公司煤改电项目","市供电公司",560,"将8个供电所8台燃煤锅炉合计2蒸吨全部更换成电锅炉","2015-10-01"]
["三、天然气项目"]
[1,"三河新源第一供热厂项目","三河新源供热有限公司",31000,"安装4X116MW燃气锅炉及其配套设施，同时敷设主干线。","2016-10-01"]
["四、生物质类项目"]
[1,"三河天龙新型建材有限公司规模化生物天然气工程","三河天龙新型建材有限公司",11280.62,"项目建设水解系统3套，一体化CSTR厌氧发酵罐9座，每座容积3170立方米，配套固液分离系统3套，沼气净化系统1套，固态和液态有机肥生产线各1套。","2017-03-01"]